Integration of Mental Health services in Havering

Planning Document

Table of Contents

1. Background information	4

2.Aim and Objectives	5

3. Rationale	6

4. Service Models	6

5. Service Profile	7

6. Service Implementation	8

7. Resource Allocation	10

8. Budget Preparation and Negotiation	12

9. Final Agreement	13

10. Project outcomes	13

11. Defining the Key Performance Indicators (KPIs)	13

References	14

# 1. Background information

1.1 Mental Health problem in the London Borough of Havering

Mental health issues have increased considerably in the past years (BMA, 2024). National Health Service (NHS) places mental health as a top priority, striving to provide excellent mental health care for all the people in need. The NHS Long Term Plan facilitates access to a high quality of care, increasing funding and developing mental health services in the hospitals as well as in the communities (NHS.UK, 2019 a). The integration of mental health services in GP clinics becomes crucial as a result of frequent concerns that NHS is facing, such as delayed access to mental services, fragmented care, the insufficient funds (TUC.ORG.UK, 2018). The available data offered by the Joint Strategic Needs Assessment (2022) reveals that 1 in 6 adults are experiencing poor mental health condition. These statistics are concerning because these mental conditions are resulting in higher cost of healthcare, poor health outcomes and decreased wellbeing of the people within community. Havering is a borough situated in East London with a population of 260 thousand people (Office for National Statistics, 2022). Despite the fact that this borough is trying to overcome the challenges regarding mental health services, it is still facing barriers regarding insufficient resources, shortage of a mental health professionals and mental illness stigma. Moreover, Havering have a diverse population with different backgrounds, beliefs and mental health needs (Office for National Statistics, 2022). All these led in complications regarding the efficient delivery of mental health services. Crucial regulation that supports the integration of mental health services, is Health and Social Care Act 2022. Under the provision of this Act mental health is a legal obligation of the council and NHS. They are responsible to assist and provide support for those who are facing mental health issues (Local Government Association, 2023).

1.2 Catchment Area Definition & Stakeholder Involvement

Another important part in planning the integration of mental health services is the consideration of relevant stakeholders. The potential stakeholders included in this project are Local Health Authorities, the Community, Government Agencies, General Practitioners, Mental Health Professionals, Volunteering Organisations and Patients and their families. The catchment area for this project includes two GP surgeries in Havering Borough. This service will be provided to the Havering Borough and surrounding areas with specific demographics and healthcare needs as the proposed catchment area. According to Havering.GOV.UK (2023), the predominant ethnicity in Havering is White British followed by Asian and other White. This statistic shows that the percentage of White Britons is higher than the London average. Moreover, the health status in Havering is recorded as good or very good. The percentage of disabled people is slighter lower than London, and life expectancy at birth increased over the past 10 years (Havering.GOV.UK, 2023).

1.3 Needs Assessment

According to NELFT Foundation Trust (2024) in Borough of Havering are established only three Mental Health and Wellness Teams that offer to patients’ mental health services. Those services cover the South, Central and North of the borough, but it could be stated that is not enough for the population that live in Havering.

This project aims to resolve several gaps in mental health services provided in London Borough of Havering. For example, the next challenges were found:

- The services are difficult to access for everyone because of the location

- The services and treatment are not timely received by the users

- Shortage of healthcare professional

- No collaboration between GP surgery, community and mental health services

# 2. Aim and Objectives

2.1 Aim

To improve the accessibility to mental health services and to enhance the mental health outcomes of the population in Havering Borough through the increasing quality of mental health services.

2.2 Objectives

- To build two units of mental health services (integrated within GP surgeries) in Havering area in 2 years

- To reduce severe mental health issues by 30% in next 3 years

- To refer 80% of patients over 65 years with dementia and related mental health issues within 2 hours for specialist mental health assessment

- To enrol 30,000 mental health patients in the first year of the service integration.

# 3. Rationale

London Borough of Havering is facing challenge regarding high percentage of elderly people, increased demand for mental health support as well as timely access to treatment and services. The integration of two units of mental health services within GP’s surgeries in Havering is crucial in order to address the needs of the people such as easy accessibility of the services, as well as the need for integrated care. Integrating these two units of mental health service is aimed to overcome all those barriers related to long time referrals, difficult access of the services and fragmented care. Moreover, these two units will provide support to the patients in their familiar environment and they will receive early intervention and better mental health outcomes.

# 4. Service Models

The project will adopt flexible service models as face-to-face consultations and home visits to ensure that covers all the needs of the population. The face-to-face consultations are meant for those patients who do not have any mobility issue. This appointment will be held to the GP surgery, in a familiar and comfortable environment in order to discuss their concerns and receive the necessary treatment. The home visits will be offered to those that cannot attend at the surgery. In this category will be included the patients with severe mobility issues, chronic illnesses or elderly people. The mental health professionals are required to assess the needs of the patients and provide support in the comfort of the patient home. Adopting those two different service models will ensure that all the preferences and needs of the people are covered.

One representative example of inclusion of mental health services in GP surgeries is Primary Mental Care Services. They successfully implemented mental health services around Peterborough and Cambridgeshire. They have set KPIs and their reports revealed a high rate of success in treating mental health illnesses. Their targets were not only reached, but they were exceeded which make them a model for NHS (NHS.UK, 2019 b).

# 5. Service Profile

| Face-to-face consultation |  |  |
| --- | --- | --- |
| Physical Requirements | Personnel | Resources |
| -quiet and confidential area - consultation rooms within GP surgery - furniture for consultation rooms - necessary equipment -computer with internet access -assessment tools (diagnostic manual, questionnaire, rating scales) | - qualified mental health professionals (nurses, psychologist, psychiatrist) - administrative staff (appointments scheduling, patients records) | - materials used during therapies -medication - brochures, informational leaflets - cleaning and disinfection supplies -hand washing facilities |

| Home visit |  |  |
| --- | --- | --- |
| Physical Requirements | Personnel | Resources |
| - portable equipment - assessment tools (questionnaires, rating scales) | - qualified mental health professionals (psychiatrists, nurses and mental health coordinators) - administrative staff (appointments scheduling, patients records and coordination) | - materials used during therapy - brochures, informational leaflets |

# 6. Service Implementation

The implementation of the project could be split in several stages. First step of Integration of Mental Health Services in Havering is planning and involving the stakeholders. Then various consultations will be held with the healthcare providers, community and service users in order to assess their needs. Development of the infrastructure as well as resource allocation is also crucial for this project. The suitable space for mental health services will be found and the qualified staff will be hired. Will be followed by models to test the delivery of services and improving the services through user’s feedback. The staff involved will have a crucial stake in the project. For example, psychiatrists and psychologists will work collaboratively in order to conduct thorough assessments and mental health evaluations of the patients. Moreover, they will provide counselling and they will prescribe the suitable medication. Nurses will assist and monitor the patient care progress through home visits, when necessary, they will administer medication and provide support during the therapy. Mental health coordinators will be in charge of coordinating appointments, facilitate patients transition and provide administrative support to the team. The implementation of the project will expand during a 2-year period.

6.1 Timeline

Integration of two units of mental health service in Havering

| Phase | Activity | Timeline (months) |
| --- | --- | --- |
| Planning of the project | Assessment of the needs | 1-2 |
|  | Stakeholder meeting | 2-3 |
|  | Establish objectives and goals | 3-4 |
| Preparation | Staff training | 5-6 |
|  | Refurbishment | 5-9 |
|  | Equipment procurement | 7-9 |
| Integration | Program launch | 10-12 |
|  | Data collection and evaluation | 12-15 |
|  | Feedback | 14-16 |
| Expansion of services | Expanding services | 17-18 |
|  | Additional staff recruitment | 18-20 |
|  | Community outreach | 19-22 |
| Evaluation of the services | KPI review | 23-24 |
|  | Final adjustments | 23-24 |
|  | Final documentation | 23-24 |

# 7. Resource Allocation

| Primary Care Facility for Mental Health Services 2024-2026 Budget Proposal |  |  |  |  |
| --- | --- | --- | --- | --- |
| Organisation Name: Primary Mental Health Services Contact person: Adriana Patru Email address: pat63175@lsme.acu.uk Total amount: 2000000 Starting date: 7/4/2024 Ending date: 7/4/2026 |  | Title Department: Department of Health Phone no: 0216548764 |  |  |
| Expenses | Description |  | Amount per year | Total amount |
| Capital investments Renovation Facility Equipment and technology | - refurbish of 2 consultation rooms with waiting areas - 2 toilets rooms with hand washing facilities |  | 400.000£ | 400.000£ |
|  | - 2 mini vans used for transportations of the patients |  | 60.000£ | 60.000£ |
|  | - furniture including (chairs, tables, curtain, cabinets, carpets, notice boards) |  | 100.000£ | 100.000£ |
|  | - 2 laptops |  | 1200£ | 12.700£ |
|  | - 2 software programs |  | 10.000£ |  |
|  | - 2 printers |  | 600£ |  |
|  | - 2 scanners |  | 600£ |  |
|  | - 2 landline phones |  | 300£ |  |
| Salaries | - 2 psychiatrists |  | 160.000£ | 320000£ |
|  | - 2 psychologists |  | 160.000£ | 320000£ |
|  | - 3 nurses |  | 120.000£ | 240000£ |
|  | - 2 mental health coordinators/ administrative staff |  | 60.000£ | 120000£ |
| Staff training | - 1 months ongoing training - 2 specialised trainers |  | 4.000£ | 4000£ |
| Consumables | - stationary - medication - PPE - cleaning materials - vehicle maintenance - petrol - building maintenance - meeting expenses - materials used during therapy |  | 40.000£ | 80.000£ |
| Miscellaneous | - unexpected expenses about 20% from total budget |  | 400.000£ | 400.000£ |
| Total amount proposed for two mental health units 1.981.100 £ |  |  |  |  |

(Kawohl et al, 2005)

# 8. Budget Preparation and Negotiation

The total amount budget proposal will be 1.000.000£ for each unit of primary mental health service within the London Borough of Havering. That amount will be funded by the Department of Health England. The preparation of the budget will be made based on the rational budget, zero-based approach (Cusworth and Franks, 2013). In order to support the whole process of budget negotiation will be held numerous meetings with the top manager, suppliers and stakeholders. Firstly, the budget will be broken down, the stakeholders will be identified and their priorities will be highlighted. Furthermore, the overview of the budget will be presented to all stakeholders, and the attention will be focussed on the anticipated benefits of the project. All the concerns about the budget and expenditures of the stakeholders will be discussed, addressed or negotiated during meetings. At the same time, stakeholders will be encouraged to work in collaboration and give feedback on the proposed budget (Graham, 2015). The negotiation with suppliers will start at the beginning. Information regarding the refurbishment services, the personnel salaries and equipment will be obtained through consultation with the Cambridgeshire and Peterborough NHS Trust team that have successfully integrated mental health into their GP services. Also for example, for equipment and refurbishment services the manager will request different quotes from vendors and different companies. After thorough investigations and receiving the quotes, the prices will be compared and the best ratio quality-price will be chosen. The suppliers will receive the requirements and timeline of the project and term and conditions will be negotiated. Furthermore, all the negotiations will be documented. Negotiation of the salary with the staff will be done by requesting one to one meeting with each employee in order to obtain the appropriate amount of annual salary. Negotiation with the top manager is a crucial step of this stage because they are responsible to approve the overall budget. During negotiation with the manager, it is important to highlight the importance of integrating mental health services in Havering as well as the positive impact on the community’s mental health and well-being. The proposed budget will be presented to the top manager, as well as the cost estimates for refurbishing, equipment, staff and training. Furthermore, all the concerns of the manager about budget constrains will be addressed.

# 9. Final Agreement

Once the budget negotiation process has ended, the next stage will be the finalisation of the agreement. All the agreements will be written in documents including the prices together with the payment’s dates. Before signing contracts with suppliers, it will be carefully reviewed to ensure clarity and understanding of the obligations and expectations for all the parties.

# 10. Project outcomes

- to reduce the mental health concerns

- develop infrastructure for mental health services

- to improve the quality of mental health services

# 11. Defining the Key Performance Indicators (KPIs)

In order to evaluate the progress of the project several Key Performance Indicators that align with the project objectives will be defined as it follow:

- number of mental issues and suicidal attempts reported and this should drop by 30% within the first year

- patient satisfaction survey will be conducted and this should confirm in 50 % increase in quality of mental health services in the first year

- the number of patients enrolled within 1 year (proposed to 30.000)

- number of referrals of elderly people within 2 hours (proposed to 80%) will also be assessed by considering hospital and care home records.

11.1 Monitoring process

The monitoring process will take place with using systems that are meant to track progress using KPIs. Relevant data will be collected and analysed regularly to assess progress and to identify the deviations from the project. In this way all the issues and risks will be identified on time (Newton Martin, 2022). Furthermore, all the issues will be promptly addressed in order to prevent the escalation. All the stakeholders will be informed about project progress and challenges encountered trough reports and updates.

This project will foster a culture of continuous improvement where the stakeholders feedback and transparency are used as main practice in all the project stages. In order to enhance effectiveness of the project it will be reviewed and updated when requested.

# References